## CAP Actions
Action No | Section | Action | Type | Action for | Status
CAP2 | Intent Costs | Proposal must include both options for delivering intent (1) Using the existing Intent model at Bupa and building on it and (2) Using intent from Amazon Connect | Action for BAFO | CAP
CAP18 | GAP in costs | Verint have only costs for voice channels, this is a Gap, we want costs for all channels (Digital - chat, email haven't been included), CAP/Verint to revise pricing and include this in the BAFO | Action for BAFO | CAP/Verint
CAP21 | Costs GAP | CAP have costed for the framework, they have not factored in integrations for data from eGain/Omni channels or Verint, action for CAP to include these costs in the BAFO | Action for BAFO | CAP
CAP22 | Costs GAP | Bupa doesn’t currently have scripts built which stiches the data together, which is one of our key requirements, CAP to ensure costs are included for building scripts and stitching data together | Action for BAFO | CAP | In Progress
CAP37 | Non Geo Numbers | Non Geo Numbers: We have 2,000 of these, we don’t use this amount but gives us flexibility to repoint when needed. CAP confirmed we don’t need surplus numbers, we can get numbers quickly from AWS through the console (2 mins). Action for CAP to use 830 Non Geo numbers for their BAFO costs. | Action for BAFO | CAP
CAP60 | Lambda costs | Assuming 1 lambda per call (seems low based on not doing the 7 improvements) – Likely more than 1 lambda functions happening . CAP to revisit this in the costs | Action for BAFO | CAP
CAP62 | IVR Assumptions | CAP to revisit the assumptions as assumed a lot would be handled by the IVR (wont happen with automations not happening. CAP to address in the BAFO | Action for BAFO | CAP
CAP63 | Verint users | Verint costs based on 1150 concurrent (modify this to reflect – 1,800 on Verint side). CAP to address in the BAFO | Action for BAFO | CAP
CAP64 | Voice Utterance | Voice utterances – 3m – CAP to revisit this and update in the BAFO | Action for BAFO | CAP
CAP66 | Implementation breakdown | Bupa will need to see the implementation proposal and a statement of work which details how this cost is broken down in the platform run and support cost figure. Cap to address in the BAFO | Action for BAFO | CAP | In Progress
CAP69 | Statement of work | Statement of work required for the BAFO with implementation proposal | Action for BAFO | CAP
CAP15 | APIs List | CAP to supply list of API's and detail so we can confirm if the current scope of work is adequate | Action for this week | CAP | Shashi Review Pending
CAP16 | Verint | Bupa's view is existing processes and integrations will remain and data going into Verint shouldn’t change - Verint engineer to confirm that this is the case. | Action for this week | CAP/Verint | Waiting for Verint's response
CAP19 | Verint Customisation costs | Verint to confirm if any customisation has been included in the proposal | Action for this week | CAP/Verint | Waiting for Verint's response
CAP27 | Out of box reports | CAP to share the out of the box reports | Action for this week | CAP | Shashi Review Pending
CAP34 | Edge | CAP to confirm if Edge is supported. It isn't for eGain at present. | Action for this week | CAP | Send email to eGain | eGain version for Amazon Connect
CAP65 | Automation assumptions | CAP to send through their assumptions so we can review the automation assumptions | Action for this week | CAP | Shashi Review Pending

## CAP Workshop Actions_Statements
Action No | Section | Action | Type | Action for
Section 1 - Overview of existing Voice/Omni Integrations and Call flows |  |  |  |  | BUPA ACTION
CAP1 | Nuance | CAP do not need to worry about the decommissioning of Nuance, this is a BUPA task. | Statement | Statement | CAP ACTION
CAP2 | Intent Costs | Proposal must include both options for delivering intent (1) Using the existing Intent model at Bupa and building on it and (2) Using intent from Amazon Connect | Action for BAFO | CAP
CAP3 | Intent Detail | Bupa to share with CAP what we currently have for Intent, they need to understand the existing engine and number of API's | Action | BUPA
CAP4 | Intent | When we develop intent for a customer that intent should be used for other channels as well (i.e. chatbot and Voice, webpage etc) – It should be the same intent engine (channel agnostic). | Statement | Statement
CAP5 | Voice Biometrics | Voice biometrics is a day 2 requirement, we want the capability but should not be costed in the BAFO | Statement | Statement
CAP6 | SMS | SMS is out of scope | Statement | Statement
CAP7 | Call Flows Summary | CAP to send a summary of what is the bare minimum they will need to give is a better understanding of costs to untangle the CISCO platform (CAP to look to work out small, medium and large change costs) | Action Complete | CAP
CAP8 | Call Flows | Bupa to supply details based on the response from CAP7 on call flows | Action | BUPA
CAP9 | PCI Pal | Proposal for PCI Pal includes digital as well, irrespective of what desktop the user has they can use the solution i.e. CRM, eGain desktop, Amazon desktop) | Statement | Statement
CAP10 | PCI Pal | CAP will define an end point that they will send to Bupa, Bupa development required on this. | Statement | Statement
CAP11 | PCI Pal | IVR payments have not been scoped as part of this project. | Statement | Statement
Section 2 - Overview of the existing WFM integrations
CAP12 | APIs | APIs are used for data sets into Verint and APIs can be called whenever they are needed | Statement | Statement
CAP13 | APIs | CAP will give us open APIs for us to consume and this is in scope of the proposal, we will consume and the cost is on Bupa | Statement | Statement
CAP14 | Customisation Questions | CAP to send us a list of questions so they can understand if there is anything that required customisation on Bupa side | Action Complete | CAP
CAP15 | APIs List | CAP to supply list of API's and detail so we can confirm if the current scope of work is adequate | Action for this week | CAP
Section 2 - Overview of the Analytic and AQM integrations
CAP16 | Verint | Bupa's view is existing processes and integrations will remain and data going into Verint shouldn’t change - Verint engineer to confirm that this is the case. | Action for this week | CAP/Verint
CAP17 | Verint | What Bupa currently has now we don’t want to lose any of this within Verint | Statement | Statement
CAP18 | GAP in costs | Verint have only costs for voice channels, this is a Gap, we want costs for all channels (Digital - chat, email haven't been included), CAP/Verint to revise pricing and include this in the BAFO | Action for BAFO | CAP/Verint
CAP19 | Verint Customisation costs | Verint to confirm if any customisation has been included in the proposal | Action for this week | CAP/Verint
CAP20 | Verint upgrades | Verint stated the majority of patch upgrades (unless major) shouldn’t result in the desktop needing to be upgraded (this is not what currently happens with KCOM when we have to do a lot of patching) | Statement | Statement
Section 4 - Integrations for MI
CAP21 | Costs GAP | CAP have costed for the framework, they have not factored in integrations for data from eGain/Omni channels or Verint, action for CAP to include these costs in the BAFO | Action for BAFO | CAP
CAP22 | Costs GAP | Bupa doesn’t currently have scripts built which stiches the data together, which is one of our key requirements, CAP to ensure costs are included for building scripts and stitching data together | Action for BAFO | CAP
CAP23 | CRM | CRM is out of scope for integration, Bupa don’t see the value of integration based on CAPs response that we will still have the same issues as today of not being able to identify the customer easily. | Statement | Statement
CAP24 | WFO | We currently get the telephony data into WFO, on the CAP solution they have WFO data going into telephony, what's the value in this? | Statement | Statement
CAP25 | Data warehouse | CAP confirmed we can takes feeds direct into our data warehouse | Statement | Statement
CAP26 | CAP detail | CAP to send an email with that they need from Bupa to cost the solution | Action Complete | CAP
CAP27 | Out of box reports | CAP to share the out of the box reports | Action for this week | CAP
CAP28 | Follow up Session | 30 min follow up session to be put in diary next week to address MI gaps and to go through more detail | Action | BUPA
Section 5 - Networks connectivity and Desktops
CAP29 | Minimal Change | CAP expect very little to change, they will provide a direct link into AWS | Statement | Statement
CAP30 | Zscaler | They have knowledge of our Zscaler so can configure | Statement | Statement
CAP31 | Firewalls | Expect some internal and 3rd party firewall changes | Statement | Statement
CAP32 | Connectivity | Home workers wont go over VPN, office will be UKLMPS, Home will be Citric connected or direct to their devices, VPN into AWS | Statement | Statement
CAP33 | PCI Pal | PCI Pal integration for eGain - This is irrelevant as this will be done in the workflow on the screens and not in eGain | Statement | Statement
CAP34 | Edge | CAP to confirm if Edge is supported. It isn't for eGain at present. | Action for this week | CAP
CAP35 | Costs Proposal | CAP confirmed the below has been factored into the proposal: 1. Chat to Voice 2. Through VA (i.e. .co.uk) 3. Comes in from VA, escalate to agent on a queue and then into voice | Statement | Statement
Section 6 – Volumetrics
CAP36 | NGN | NGN Numbers wont change - These will just be repointed to the platform | Statement | Statement
CAP37 | Non Geo Numbers | Non Geo Numbers: We have 2,000 of these, we don’t use this amount but gives us flexibility to repoint when needed. CAP confirmed we don’t need surplus numbers, we can get numbers quickly from AWS through the console (2 mins). Action for CAP to use 830 Non Geo numbers for their BAFO costs. | Action for BAFO | CAP
CAP38 | Call Flows | Call flows 500, modular concept so don’t scope for 500 as this will be less in the final solution | Statement | Statement
CAP39 | AHT Request | Bupa to supply AHT for the Bupa categories (i.e. for the SERV_ cats etc) | Action | BUPA
CAP40 | Peak periods | Inbound calls - Jan to Easter is the busiest period (corp renewals). Remains relatively busy up to August and then drops during school holidays, then picks up to the autumn and then drops near Christmas | Statement | Statement
CAP41 | Categories | Bupa confirmed we have a lot of categories as this is how we structured ourselves | Statement | Statement
CAP42 | Abandoned calls | Bupa doesn’t have a process to monitor abandoned calls, customer tends to call back, scheduled call backs and workflow is something we want. | Statement | Statement
CAP43 | Benefits not to be factored into costs | A lot of initiatives in Bupa to try and fix number of calls backs which is already factored into Benefits, Bupa stated to CAP do not factor in the cots how much money you will think you will save. | Statement | Statement
CAP44 | Charges | CAP confirmed we will be charged when a customer is in the queue (no differentiation between chatting with an agent or waiting). Costs could be reduced here by queued call backs. | Statement | Statement
CAP45 | Internal Costs | Internal costs are neutral bar the service charge | Statement | Statement
CAP46 | Skill Groups | Skills groups 712 - This can be simplified as was based on an onprem model and includes overflow scripts. | Statement | Statement
CAP47 | AWS Bill breakdown | CAP confirmed the bill for costs will be broken down so we have clear visibility on what we have been charged for | Statement | Statement
CAP48 | Contact Lense | Contact Lenses will give us an enhanced level of data (costed in the proposal) | Statement | Statement
CAP49 | Nice figures request | Bupa to send CAP the nice figures | Action | BUPA
CAP50 | Outbound calls | Outbound calls - CAP to cost on 338,000 (ish) the numbers in the sheet provided, these are all agent initiated | Statement | Statement
CAP51 | Costs Spreadsheet tab 1 | No of agents is concurrent agents | Statement | Statement
CAP52 | Costs Spreadsheet tab 1 | AHT Inbound (300) - This is based on 7 areas where CAP flagged automation could be done. Bupa confirmed this should be set at 500 and CAP to refine costs for the BAFO based on this | Statement | Statement
CAP53 | Costs Spreadsheet tab 1 | Acqueon Outbound dialler - This is separate calculation which isn't included in this sheet, CAP to include this in the BAFO | Statement | Statement
CAP54 | Costs Spreadsheet tab 1 | All agents can take payments but are only charged when they take a payment | Statement | Statement
CAP55 | Costs Spreadsheet tab 1 | £1,058 is flat pricing, charged this regardless so not based on consumption | Statement | Statement
CAP56 | Costs Spreadsheet tab 1 | 85,976 – This Is based on assumption we have worked out (based on consumption) | Statement | Statement
CAP57 | Costs Spreadsheet tab 1 | £74.76 – CAP confirmed this Includes everything bar the MI. | Statement | Statement
CAP58 | Costs Spreadsheet tab 1 | 5% allowance – just fat within the model | Statement | Statement
CAP59 | Costs Spreadsheet tab 2 | All pricing is in pounds | Statement | Statement
CAP60 | Lambda costs | Assuming 1 lambda per call (seems low based on not doing the 7 improvements) – Likely more than 1 lambda functions happening . CAP to revisit this in the costs | Action for BAFO | CAP
CAP61 | ACD | ACD table – when we land with an agent (true cost is ACD plus IVR) | Statement | Statement
CAP62 | IVR Assumptions | CAP to revisit the assumptions as assumed a lot would be handled by the IVR (wont happen with automations not happening. CAP to address in the BAFO | Action for BAFO | CAP
CAP63 | Verint users | Verint costs based on 1150 concurrent (modify this to reflect – 1,800 on Verint side). CAP to address in the BAFO | Action for BAFO | CAP
CAP64 | Voice Utterance | Voice utterances – 3m – CAP to revisit this and update in the BAFO | Action for BAFO | CAP
CAP65 | Automation assumptions | CAP to send through their assumptions so we can review the automation assumptions | Action for this week | CAP
CAP66 | Implementation breakdown | Bupa will need to see the implementation proposal and a statement of work which details how this cost is broken down in the platform run and support cost figure. Cap to address in the BAFO | Action for BAFO | CAP
Section 7 - Suggested Migration order of events
CAP67 | Implementation breakdown | Bupa to highlight on the sheet what isnt relevant for CAP | Action | BUPA
General Actions
CAP68 | CAP actions summary | CAP to send all final list of questions/queries to Bupa by EOB (22nd July) | Action Complete | CAP
CAP69 | Statement of work | Statement of work required for the BAFO with implementation proposal | Action for BAFO | CAP
CAP70 | Commercials | Commercials will be fixed to the scope so CAP/Bupa are confident what is being proposed. | Statement | Statement
CAP71 | Bupa pack Bundle | BUPA will bundle up packs/information and send to CAP for the BAFO | Action | BUPA

## CAP Questions to Bupa
CAP QUESTION | BUPA RESPONSE
1 "We need the list of MI data points captured currently within the existing system - Showcased number of MI reports. Can you provide exact business MI requirements - Share Data Sources from where current PowerBI reports are aggregated"
2 "What percentage (%) of existing contact flows could be retired/decommissioned?
3 What is the total number of IVRs, please provide the documentation presented
4 What is the total number of Contact Flows, please provide the documentation presented
5 How does Bupa split their contact centres (by operation / geography etc) - number of agents in each and key lines of business
6 "Migration - Bupa have mentioned 6-8 phases - How do you envisage the transition (ie what is the split) - scope of each phase and the expected timeline of the phases"
7 Can we get AHT for specified call categories e.g. sps_msk
8 Can we get number of integrations (touchpoints) for each category
9 Within these categories where does Bupa see the greatest potential for automation and self service
10 Monthly call distribution fairly even in 2019, are the monthly variances in 2020 primarily COVID related?
11 "Why is January 2021 volumes lower than expected? Are we seeing similar (lower) volumes Feb – July?"
12 Since current Chat (with eGAIN) is using different intent engine and Voice will use AWS Lex based intents, we would need to plan Phase 2 of aggregation of all Intents to come from same engine - Please clarify if this effort should be factored in the current proposal?
13 Confirm the automated outbound calls are made to confirm if an Outbound Dialler solution is needed or we can depend on agents to make calls from CCP

## CAP27 - Reports
Sl. No | Report Name | Details
1 | Real-time metrics reports | Real-time metrics reports show real-time or near-real time metrics information about activity in your contact center. Metrics such as Online show the number of agents currently online in real-time, updating every 15 seconds. Metrics such as Handled and Abandoned reflect near real-time values for your contact center.
2 | Historical metrics reports | Historical metrics reports include data about past, completed activity and performance in your contact center. Amazon Connect includes built-in historical reports that you can start using right away. These reports contains CTR-driven metrics These metrics are based on formed CTR records. For a given interval, CTRs whose disconnect date falls in the interval are selected to calculate metrics. For example, if a contact starts at 05:23 and ends at 06:15, this contact contributes 52 minutes of metrics for the 06:00-06:30 interval. Example CTR-driven metrics are Service level, Agent interaction time, and After contact work time. Agent activity-driven metrics These metrics are based on agent activities, like agent status changes, agent conversation changes. The metrics reflect on the actual time the activity happens. For example, if agent handles a contact from 05:23 to 06:15, the Agent on contact time has 7 minutes for the 05:00-05:30 interval, 30 minutes for the 05:30-06:00 interval, and 15 minutes for the 06:00-06:30 interval. For example, an agent activity-driven metric is Non-Productive Time.
3 | Login/Logout reports | The Login/Logout report displays the login and logout information for the users in your contact center (for example, agents, managers, and administrators). For each user session, the login and logout times are displayed as a row in the report. You can use the report to determine the time users were logged in to Amazon Connect. The report also displays the amount of time for each session that user was logged in to Amazon Connect. Login/Logout report limit: 10,000 rows
4 | Custom Reports | Amazon Connect Service APIs can be used to create custom reports, such as real-time reports that are filtered by teams of agents
5 | Verint Standard Reports | These can be run on a schedule, results delivered to the user within the application or via e-mail. Typically used for operational management, the results can be exported for use in 1-2-1s or manipulated in Excel
6 | Verint Ad hoc reports | The customer is able to create their own “ad hoc” reports using the Verint data model, this is typically used to create new and different views of the data from standard reports
7 | Verint Custom extracts | In the event that the data required by the customer is not published in an API or standard method, Verint can create customised extracts and make this available for their usage
8 | eGain Activity Classification Reports | These historical reports provide information about count of completed activities that were categorized with the Classification and Resolution code
9 | eGain Activity Routing Reports | These historical reports provide information about the queuing and routing of chat, email and other activities
10 | eGain Agent by Call Type Reports | These historical reports provide information about agnet by call type | There are many more reports which can be generated from eGain. Refer the guides attached
11 | eGain Agent Event Details Reports | These historical reports provide information about agnet event data for agents
12 | eGain Agent Event Reports | These historical reports provide information about detail agent events (login/logout,not ready etc) and durations
13 | eGain Agent Logout Reports | These historical reports provide information about detail agent login/logout events specifically. Timestamp and occurrence of each events are also shown.
14 | eGain Agent Productiveness Reports | These historical reports provide information about productiveness metrics for agents
15 | eGain Agent Session Summary Reports | These historical reports provide information about agent login sessions for chat and emails | eGain
16 | eGain Agent Skillgroup Times Reports | These historical reports provide information that detail agent performance (call handled, talk time, hold time, wrap time, % available, etc.) either as an aggregation of the agent regardless of the skill group assignments or on a per skill group basis. | PCI Pal
17 | eGain Agent State Trace Reports | These historical reports provide information about agent state data for Unified CCE agents. | Acqueon
18 | eGain Agent Times Reports | These historical reports provide information about data for Agents.
19 | eGain Amazon Agent Offline Summary Reports | These historical reports provide information about aggregated overview of time spent by Agents in different offline codes.
20 | eGain Amazon Agent State Detail Reports | These historical reports provide information about detailed reporting of the duration and transition time of different agent states.
21 | eGain Amazon Agent Summary Reports | These historical reports provide information about aggregated contact handling metrics such as volumes, dispositions, handling times ,summarized by Agent.
22 | eGain Amazon Contact Detail Reports | These historical reports provide information about detailed level view of each individual contact.
23 | eGain Amazon Contact Routing Summary Reports | These historical reports provide information about aggregated routing metrics such as volumes, dispositions, wait times, handling times, dispositions summarized by DN, Source/Target Queue, Source/Target Agent, Call Variable dimensions, call counts and VRU/handle time durations.
24 | eGain Amazon Dialed Number Summary Reports | These historical reports provide information about aggregated contact treatment metrics such as volumes, dispositions, wait times, handling times and service level, summarized by Dialed Number.
25 | eGain Amazon Queue Summary Reports | These historical reports provide information about Aggregated routing metrics such as volumes, dispositions, wait times, handling times, dispositions and service level, summarized by Queue.
26 | eGain Call Detail End Reports | These historical reports provide historical call end data.
27 | eGain Call Detail Leg Reports | These historical reports provide historical call leg data.
28 | eGain Call Journey Reports | These historical reports provide information about event data defining all repeat and non-repeat (First Call Resolution or Abandon) interactions (voice, email, chat etc) in the system.
29 | eGain Call Type Skillgroup Times Reports | These historical reports provide information about data for Call Types and Skill Groups.
30 | eGain Calls By Call Type Reports | These historical reports provide information about call type performance (calls offered, calls abandoned, handle durations, service level, trends, etc.).
31 | eGain Calltrack Activity Reports | These historical reports provide information about analyzing the handling of CallTrack activities in the Advisor Desktop and workflow.
32 | eGain Campaign Query Rule Reports | These historical reports provide information about detail outbound campaign call dispositions.
33 | eGain Case Activity Reports | These historical reports provide information about the assignment and closure of email, chat and other activities.
34 | eGain Case Resolution Reports | These historical reports provide information about analyzing case closure, reopens and first contact resolution rates.
35 | eGain Chat Activity Reports | These historical reports provide information about the handling of chat activities.
36 | eGain Chat Serviced and Abandon Intervals Reports | These historical reports provide information about chats serviced or abandoned in service level.
37 | eGain Cobrowse Session Detail Reports | These historical reports provide per session information on cobrowse sessions.
38 | eGain Cobrowse Summary Reports | These historical reports provide information about cobrowse sessions, agent engagement and pages navigated during the cobrowse sessions.
39 | eGain Concurrent Channel Usage Reports | These historical reports provide information about concurrent channel usage.
40 | eGain CVP Usage Reports | These historical reports provide information about Unified CVP usage.
41 | eGain Dialer Details Reports | These historical reports provide information about outbound dialers.
42 | eGain Email Activity Reports | These historical reports provide information about the handling of email activities.
43 | eGain Email Inventory By Age Reports
44 | eGain Guided Help Effectiveness Reports | These historical reports provide information about the effectiveness of guided help sessions.
45 | eGain IVR Application Summary Reports | These historical reports provide information about data for IVR Applications.
46 | eGain IVR Application Times Reports | These historical reports provide information about data for IVR Applications.
47 | eGain IVR Call Detail Reports | These historical reports provide information about data for IVR Calls.
48 | eGain IVR Call Times Reports | These historical reports provide information about data for IVR Calls.
49 | eGain IVR Call Reports | These historical reports provide information about data for IVR Calls.
50 | eGain IVR Callback Detail Reports | These historical reports provide information about data for IVR Callbacks.
51 | eGain IVR Callback Summary Reports | These historical reports provide information about data for IVR Callbacks.
52 | eGain IVR Node Reports | These historical reports provide information about data for IVR Node/Element interactions
53 | eGain Knowledge Authoring Productivity Reports | These historical reports provide information that measures the amount and effectiveness of knowledge base authoring.
54 | eGain Knowledge Base Performance Reports | These historical reports provide information about volume of article usage relating to activities arising through different channels such as email or chat and the methods by which the knowledge article was accessed.
55 | eGain Knowledge Utilisation Reports
56 | eGain Network Trunk Group Times Reports | These historical reports provide information about data for Network Trunk Groups.
57 | eGain Notify Summary Reports | These historical reports provide information about eGain Notify messages.
58 | eGain Offers Summary Reports | These historical reports provide information about the performance of offers.
59 | eGain Peripheral Times Reports | These historical reports provide information about detail peripheral level performance.
60 | eGain Precision Queue Times Reports | These historical reports provide information about metrics for Precision Queues.
61 | eGain Self Service Article Usage Reports | These historical reports provide information about the effectiveness of searches by article and the ratings given to articles by users of the knowledge base articles used in knowledge base sessions.
62 | eGain Self Service Performance Reports | These historical reports provide information about the effectiveness of the knowledge base and knowledge base articles used in knowledge base sessions.
63 | eGain Service Times Reports | These historical reports that provide information about services performance.
64 | eGain Skillgroup Times Reports | These historical reports provide information about skill group level performance (calls handled, call durations, login time etc.).
65 | eGain Social Activity Reports
66 | eGain Social Search Reports | These historical reports provide information about monitoring social activities as well as post and reply to customers on these same outlets through the Social Console.
67 | eGain Trunk Group Times Reports | These historical reports provide information about detail trunk group performance.
68 | eGain Unavailable Time By Reason Code Reports | These historical reports provide information about agent unavailability metrics.
69 | eGain Virtual Assistant Summary Reports | These historical reports provide information about historical analysis of Virtual Assistant volume and performance metrics.
70 | eGain Virtual Assistant Top Exchanges Reports
71 | eGain Agent Skillgroup Reports | These real time reports provide informatioon about Real-Time Agent Skill Group data.
72 | eGain Agent Reports | These real time reports provide information about real time agent state, current direction (inbound vs. outbound), duration in current state and timestamp of latest state change.
73 | eGain Amazon Agent Reports
74 | eGain Amazon Queue Reports
75 | eGain Call Type Reports | These real time reports provide information about real time call type performance statistics (calls offered to the 5, calls offered to the half, calls offered today, service level 5, half, today, etc.)
76 | eGain Campaign Query Rule Reports | These real time reports provide information about real time call type performance statistics (calls offered to the 5, calls offered to the half, calls offered today, service level 5, half, today, etc.)
77 | eGain Campaign Reports | These real time reports provide information about real-time metrics produced by Outbound Agents when a dialing list is executed for an outbound campaign.
78 | eGain Dialer Reports | These real time reports provide information produced by Blended (Outbound) Agent when a dialing list is executed for an outbound campaign. Each row provides statistics for an individual Dialer.
79 | eGain IVR Callback In Progress Detail Reports | These real time reports provide information about real-time metrics relating to IVR Callbacks that are currently in progress.
80 | eGain Peripheral Reports | These real time reports provide information about real-time metrics for Peripheral ACDs.
81 | eGain Precision Queue Step Reports | These real time reports provide information about real-time metrics for each step within a Precision Queue.
82 | eGain Precision Queue Reports | These real time reports provide information about real-time metrics for Precision Queues.
83 | eGain Queue Monitor Reports | These real time reports provide queue monitor information for chats, video chats, emails and tasks.
84 | eGain Service Reports | These real time reports provide information about detail services performance.
85 | eGain Skillgroup Reports | These real time reports provide information about real time agent state, current direction (inbound vs. outbound), duration in current state by skillgroup. End users can assess the overall queue state by skillgroup (call in queue, longest call waiting, etc.)
86 | eGain User Group Monitor Reports | These real time reports provide information about user group monitor information for chats, video chats, emails and tasks.
87 | eGain User Monitor Reports | These real time reports provide information about user monitor information for chats, video chats, emails and tasks.

## CAP15- APIs List
Sl.No | APIs Description | Additional Scope | Complexity
1 | APIs for retrieving tokens from ForgeRock
2 | APIs for retrieving access token from AD to connect to MS Dynamics
3 | APIs for pulling the data from MS Dynamics
4 | APIs for pushing the data to MS Dynamics
5 | APIs for pulling the data from USD
6 | APIs for pushing the data to USD
7 | APIs for pushing data to DWH (Capgemini managed Data and MI or Bupa DWH) | Y | High
8 | APIs for sending SMS via 2SMS.com | Y | Medium
9 | APIs for legacy call recording/transcript retrieval from KCOM * | Y | High
10 | APIs for PCI Pal endpoint | Y | Medium | MI Reporting from DWH
11 | APIs for payment transaction update to Bupa systems |  |  | More APIs as per the solution and new requirements
12 | APIs for getting Amazon Connect custom reports | Y | Medium | Marked with *
13 | API for sending emails |  |  | Amazon Connect APIs
14 | APIs for pulling the data from Bupa SWIFT | Y | Medium | Sppech to Text
15 | APIs for pushing the data to Bupa SWIFT | Y | Medium | Text to Speech
16 | APIs for data masking
17 | APIs for data extraction for real-time and historical analytics
18 | APIs for outbound calling
19 | APIs for MI Reporting from DWH
20 | APIs to enable configure and reuse connections to external applications
21 | API which allows to confirm that the attachment has been uploaded using the pre-signed URL
22 | API which allows the specified Amazon Connect instance to access the specified Amazon Lex or Amazon Lex V2 bot.
23 | API to creates the participant's connection
24 | API to disconnects a participant
25 | API which provides a pre-signed URL for download of a completed attachment. This is an asynchronous API for use with active contacts
26 | API to provides a list of analysis segments for a real-time analysis session
27 | API to retrieves a transcript of the session, including details about any attachments
28 | API to provides a pre-signed Amazon S3 URL in response for uploading the file directly to S3.
29 | API Allows the specified Amazon Connect instance to access the specified Lambda function.
30 | API Associates a set of quick connects with a queue.
31 | API Associates a set of queues with a routing profile.
32 | API to creates a contact flow for the specified Amazon Connect instance.
33 | API which creates a new queue for the specified Amazon Connect instance.
34 | API which creates a quick connect for the specified Amazon Connect instance
35 | API which creates a new routing profile.
36 | API which creates a user account for the specified Amazon Connect instance.
37 | API which creates a new user hierarchy group.
38 | API which describes the specified queue.
39 | API which describes the quick connect
40 | API to retrieves the contact attributes for the specified contact
41 | APIs to gets the real-time metric data from the specified Amazon Connect instance
42 | API to gets historical metric data from the specified Amazon Connect instance
43 | API to initiates a contact flow to start a new chat for the customer.
44 | API to starts recording the contact when the agent joins the call
45 | API to creates or updates user-defined contact attributes associated with the specified contact
46 | APIs for speech to text conversion
47 | APIs for text to speech conversion
48 | APIs to pull new information from USD to be shown on agent desktop | Y | Medium
49 | New APIs for Intents | Y | High
50 | APIs for pushing call transcripts to MS Dynamics | Y | High
* | We assume all the legacy call recordings migrated to Verint SaaS platform before we accept contact on Amazon Connect instance
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We assume all the legacy call recordings migrated to Verint SaaS platform before we accept contact on Amazon Connect instance

## CAP65 - Automation
Sl.No | Automation | Benefits
| Fully automated AWS Landing Zone setup using Terraform | Saves 60% time and effort for setting up new AWS landing zone for enterprise
Fully automated observability solution
Fully automated security remediation
Fully automated Dynamic DevOps Pipeline
1 | Automation for implementing self-service flows | Reduce AHT. No agent required. Better customer experience.
2 | Real time assistance to Agents for customer insight | Faster response from Agent Understanding of call intention by Agent
3 | Automate customer response by enriching VA with more intelligent IVRs | Faster response Reduce AHT. No agent required. Better customer experience.
4 | Responding to common queries by integration of chatbot to back-end systems via APIs. Removing agent intervention | Faster response Reduce AHT. No agent required. Better customer experience.
5 | Implementing interactive messages | Reduce AHT by enabling user to select options instead of typing
6 | Fully automated ID&V journey by enhancing the process using IVR. Will scope after Blueprinting phase. | No agent intervention or involvement. Reduce AHT
8 | Personalized and Dynamics Routing | Better customer experiece Less wait time for customer
9 | Skill Based Routing | Better customer experiece Less wait time for customer
10 | Use Outbound Call Queue, automated outbound calls will be initiated. | No manual initaion of outbound call by Agent No delay in outbound calling
11 | Automating the insight and response as per customer contact history | Better understanding of call intention by Agent
12 | Automating call categorization | Better QM
13 | Post call activities | Reduce agent time on post call activities
14 | Automated callback to cutomer and connects to Agents during the call drop | Reduce call volume Better customer satisfaction
15 | Automated for outbound campaign management | Better and faster customer reach. Faster campaigning
Automation using Contact Lens?